## Central
DELIVERY TRACKER (March , Week 4)
PROJECT IDENTIFICATION | [10 empty] | MILESTONE TRACKING | [8 empty] | RISK & MOMENTUM
# | Client | Project Name / Code | Service Type | Revenue Model | Delivery Manager | Client SPOC | Project Type | Resource Aligned | Handled By | Add Info | Milestone | Revenue | Milestone Description | Planned Start | Planned End | Actual Start | Actual End / ETA | % Complete | Deliverable(s) | Milestone Flag | Days Variance | Current Status | Blocker (Y/N) | Blocker Owner | Remarks / Action | Inv status
1 | Novartis | ITSE Dashboard | Outcome | Milestone | Anuradha Murthy | Rashim Chaudhary | Data Analysis & Dashboarding | Mriganka | Wipro | NA | M1 |  | Verification and SOW | 2025-12-12 | 2026-01-10 | 2026-02-02 | 2026-02-07 | 100 | Doc | Green | 28 | Completed | N | — | Completed on time | Raised
[11 empty] | M2 |  | KPI and Mock Dashboard | 2025-12-12 | 2026-01-15 | 2026-02-08 | 2026-02-15 | 100 | Dashboard | Green | 31 | Completed | N | Client | Client delayed SOW signing | Raised
[11 empty] | M3 |  | Integration of Data + Testing | 2025-02-07 | NA | NA | NA | 0 | NA | Amber | 0 | Delayed | Y | Client | Customer responded saying they’ve moved from Snowflake to Databricks for the integration. Romit(Wipro spokesperson (lead for ITSE)) is currently coordinating with the Novartis team to enable the required access . Next update by 27/03 (pending) | Pending
2 | GE | Gate Test Maintainance | Outcome | Milestone | Sadhna Shukla | Abhishaik Srivastava | Automation | Dhinakar | Consultant | IGS | M1 |  | Quick Test Analysis | NA | 2025-09-30 | 2025-09-01 | 2025-09-30 | 100 | Run Quick tests in container & VM, compare results, analyze & categorize failures | Green | 0 | Completed | N | — | M1 delivered | Raised
[11 empty] | M2 |  | Quick Test Fixes + Slow/Very Slow Analysis | 2025-09-30 | 2025-10-31 | 2025-12-01 | NA | 40 | Fix Quick test failures, validate; then run Slow & Very Slow tests, analyze failures, fix and re-validate | Amber | 87 | Delayed | Y | Practise | 20/20 Quick + 7/7 Slow tests fixed. 87 Very Slow test scenarios pending (Config UI for distributable config settings). Running in parallel with M3. | Pending
[11 empty] | M3 |  | Dockerized Parallel Execution | NA | 2025-11-28 | 2025-12-01 | NA | 70 | Enable full parallel execution across all test tracks (Main, Quick, Slow, Very Slow) targeting multiple SUTs simultaneously; fix and validate | Amber | 116 | On Hold | Y |  | 3-container run stable: 39/39 features, 3.47hrs (20% saving). 4-container achieves 2.44hrs (44% saving) but 6 features fail due to service dependencies. Awaiting Aravinda approval to go live with 3-container. Service team alignment ongoing for 4-container. | Pending
[11 empty] | M4 |  | Code Cleanup & MR Approval | NA | 2025-12-19 | NA | NA | 0 | Final code cleanup, execution validation, merge request approval with up to 3 review iterations | Red | 0 | On Hold | Y | Practise | Dependent on M3 go-live approval and stabilization. Not yet started. | Pending
|  | AVS Scrum | Governance | Monthly | Sadhna Shukla | Mitul Agrawal | Others | NA | Internal Team | NA | M1 |  | AVS Scrum | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M2 |  |  | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M3 |  |  | 2026-02-01 | 2026-02-28 | 2026-02-01 | 2026-02-28 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M4 |  |  | 2026-03-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 0 | [7 empty] | Pending
[11 empty] | M5 |  |  | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-30 | 0 | [7 empty] | Pending
[11 empty] | M6 |  |  | 2026-05-01 | 2026-05-31 | 2026-05-01 | 2026-05-31 | 0 | [7 empty] | Pending
[11 empty] | M7 |  |  | 2026-06-01 | 2026-06-30 | 2026-06-01 | 2026-06-30 | 0 | [7 empty] | Pending
[11 empty] | M8 |  |  | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31 | 0 | [7 empty] | Pending
[11 empty] | M9 |  |  | 2026-08-01 | 2026-08-31 | 2026-08-01 | 2026-08-31 | 0 | [7 empty] | Pending
[11 empty] | M10 |  |  | 2026-09-01 | 2026-09-30 | 2026-09-01 | 2026-09-30 | 0 | [7 empty] | Pending
[11 empty] | M11 |  |  | 2026-10-01 | 2026-10-31 | 2026-10-01 | 2026-10-31 | 0 | [7 empty] | Pending
[11 empty] | M12 |  |  | 2026-11-01 | 2026-11-30 | 2026-11-01 | 2026-11-30 | 0 | [7 empty] | Pending
|  | Devops PitCrew CD Automation | Governance | Monthly | Sadhna Shukla | Abhishaik Srivastava | Others | Dhinakar | Consultant | IGS | M1 |  | Devops PitCrew | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M2 |  |  | 2026-02-01 | 2026-02-28 | 2026-02-01 | 2026-02-28 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M3 |  |  | 2026-03-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 0 | [7 empty] | Pending
[11 empty] | M4 |  |  | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-30 | 0 | [7 empty] | Pending
[11 empty] | M5 |  |  | 2026-05-01 | 2026-05-31 | 2026-05-01 | 2026-05-31 | 0 | [7 empty] | Pending
[11 empty] | M6 |  |  | 2026-06-01 | 2026-06-30 | 2026-06-01 | 2026-06-30 | 0 | [7 empty] | Pending
[11 empty] | M7 |  |  | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31 | 0 | [7 empty] | Pending
[11 empty] | M8 |  |  | 2026-08-01 | 2026-08-31 | 2026-08-01 | 2026-08-31 | 0 | [7 empty] | Pending
[11 empty] | M9 |  |  | 2026-09-01 | 2026-09-30 | 2026-09-01 | 2026-09-30 | 0 | [7 empty] | Pending
[11 empty] | M10 |  |  | 2026-10-01 | 2026-10-31 | 2026-10-01 | 2026-10-31 | 0 | [7 empty] | Pending
[11 empty] | M11 |  |  | 2026-11-01 | 2026-11-30 | 2026-11-01 | 2026-11-30 | 0 | [7 empty] | Pending
[11 empty] | M12 |  |  | 2026-12-01 | 2026-12-31 | 2026-12-01 | 2026-12-31 | 0 | [7 empty] | Pending
|  | LTS | Outcome | Milestone | Sadhna Shukla |  | Data Engineering & Automation | Dhinakar, Sharat, Kartika, Balaji | Internal Team |  | M1 |  | Foundation Complete | W0 | W3 | TBD | TBD | 0 | Requirements documented, architecture approved | [6 empty] | Pending
[11 empty] | M2 |  | LTS Orcxhestration Pipeline Ready | W3 | W8 | TBD | TBD | 0 | SBOM promotion (Phase 1) completes successfully before per-component LTS verification builds (Phase 2) are triggered | [6 empty] | Pending
[11 empty] | M3 |  | Remediation System | W8 | W10 | TBD | TBD | 0 | Log parsing and artifact promotion scripts operational | [6 empty] | Pending
[11 empty] | M4 |  | Pilot Success | W10 | W10 | TBD | TBD | 0 | 27 components automated and verified successfully | [6 empty] | Pending
[11 empty] | M5 |  | Production Ready | W10 | W11 | TBD | TBD | 0 | All testing complete, monitoring live | [6 empty] | Pending
[11 empty] | M6 |  | Full Deployment Deployment | W11 | W12 | TBD | TBD | 0 | All components live, metrics validated | [6 empty] | Pending
3 | Lowes | SEO Roadmap Deep Dive | Governance | Monthly | Mehr | Charushila Biswas | Others | Not Assigned | Internal Team | NA | M1 |  | SEO Roadmap Deep Dive | 2025-08-28 | 2025-08-31 | 2025-08-28 | 2025-08-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M2 |  |  | 2025-09-01 | 2025-09-30 | 2025-09-01 | 2025-09-30 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M3 |  |  | 2025-10-01 | 2025-10-31 | 2025-10-01 | 2025-10-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M4 |  |  | 2025-11-01 | 2025-11-30 | 2025-11-01 | 2025-11-30 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M5 |  |  | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M6 |  |  | 2026-01-01 | 2026-01-31 | 2026-01-01 | 2026-01-31 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M7 |  |  | 2026-02-01 | 2026-02-28 | 2026-02-01 | 2026-02-28 | 100 | As per client requirement | Green | 0 | Completed | N |  |  | Raised
[11 empty] | M8 |  |  | 2026-03-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 0 | [7 empty] | Pending
[11 empty] | M9 |  |  | 2026-04-01 | 2026-04-30 | 2026-04-01 | 2026-04-30 | 0 | [7 empty] | Pending
[11 empty] | M10 |  |  | 2026-05-01 | 2026-05-31 | 2026-05-01 | 2026-05-31 | 0 | [7 empty] | Pending
[11 empty] | M11 |  |  | 2026-06-01 | 2026-06-30 | 2026-06-01 | 2026-06-30 | 0 | [7 empty] | Pending
[11 empty] | M12 |  |  | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31 | 0 | [7 empty] | Pending
5 | DSGS | Pricing Engine Commercial Twin | Outcome | Milestone | Sadhna Shukla |  | AI Solution | TBD | Internal Team | NA | M1 |  | Signed-off platform spec, data readiness report, confirmed acceptance criteria, finalized tech stack | NA | NA | NA | NA | 100 | Signed-off platform spec, data readiness report, confirmed acceptance criteria, finalized tech stack | Green | [5 empty] | Pending
[11 empty] | M2 |  | Working estimation UI with activity-level output; risk buffer calculation calibration; all 6 dimensions configurable | NA | NA | NA | NA | 0 | Working estimation UI with activity-level output; risk buffer calculation calibration; all 6 dimensions configurable | [6 empty] | Pending
[11 empty] | M3 |  | Full version control, role-based access, audit trails, security hardening, and data migration complete | NA | NA | NA | NA | 0 | Full version control, role-based access, audit trails, security hardening, and data migration complete | [6 empty] | Pending
[11 empty] | M4 |  | Complete, closed-loop platform live in production; DSGS team trained; full documentation delivered | NA | NA | NA | NA | 0 | Complete, closed-loop platform live in production; DSGS team trained; full documentation delivered | [6 empty] | Pending
|  | Pricing Engine Transition Factory | Outcome | Milestone | Sadhna Shukla |  | AI Solution | TBD | Internal Team | NA | M1 |  | Signed-off platform spec, data readiness report, confirmed acceptance criteria, finalized tech stack | NA | NA | NA | NA | 0 | Signed-off platform spec, data readiness report, confirmed acceptance criteria, finalized tech stack | [6 empty] | Pending
[11 empty] | M2 |  | Working Transition Factory estimation UI with activity-level output; new model calibrated to transition domain; all 6 risk dimensions configurable | NA | NA | NA | NA | 0 | Working Transition Factory estimation UI with activity-level output; new model calibrated to transition domain; all 6 risk dimensions configurable | [6 empty] | Pending
[11 empty] | M3 |  | Unified platform with both Commercial Twin and Transition Factory modules live; full version control, role-based access, audit trails, security hardening complete | NA | NA | NA | NA | 0 | Unified platform with both Commercial Twin and Transition Factory modules live; full version control, role-based access, audit trails, security hardening complete | [6 empty] | Pending
[11 empty] | M4 |  | Complete, closed-loop platform live in production; two UAT cycles completed; DSGS team trained; full documentation delivered | NA | NA | NA | NA | 0 | Complete, closed-loop platform live in production; two UAT cycles completed; DSGS team trained; full documentation delivered | [6 empty] | Pending
|  | Deployment of the Infrastructure | Outcome | Milestone | Sadhna Shukla |  | AI Solution | TBD | Internal Team | NA | M1 |  | Proposal under work | NA | NA | NA | NA | 0 | Proposal under work | [6 empty] | Pending
[11 empty] | M2 |  |  | NA | NA | NA | NA | 0 | [7 empty] | Pending
[11 empty] | M3 |  |  | NA | NA | NA | NA | 0 | [7 empty] | Pending
[11 empty] | M4 |  |  | NA | NA | NA | NA | 0 | [7 empty] | Pending
📊 MS DELIVERY DASHBOARD
Total MS Projects | Total Milestones Tracked | Milestones Complete (100%) |  |  | Flagged Red |  | Flagged Amber |  |  |  | Avg % Completion |  | Total Contract Value ($)
0 | 61 | 16 |  |  | 1 |  | 3 |  |  |  | 28.0328 |  | #REF!